## Sheet1
Test Plan
Item | Details
Project | QA Assessment – User Profile Registration
Document | Test Plan
Version | 1
Author | Cristi Zagan
Date | 2026-07-03
Status | Final
1. Purpose
The purpose of this test plan is to define the testing strategy for the User Profile Registration page.
2. Scope
Feature
First Name validation
Last Name validation
Email validation
Password validation
Confirm Password validation
Gender selection
Date of Birth validation
Phone Number validation
Address input
LinkedIn URL validation
GitHub URL validation
Form submission
Error messages
Success message
Cross-browser compatibility
Out of Scope
Example
Item
Backend database validation
API testing
Security/Penetration testing
Load testing
Mobile application testing
3. Test Objectives
Verify mandatory fields are enforced.
Validate all input formats.
Verify optional fields accept valid values.
Verify invalid data produces appropriate validation messages.
Verify successful profile creation.
Verify browser compatibility.
Verify UI behaves consistently.
4. Test Strategy
Testing Type | Included
Functional Testing | ✔
UI Testing | ✔
Validation Testing | ✔
Boundary Value Testing | ✔
Negative Testing | ✔
Smoke Testing | ✔
Regression Testing | ✔
Cross Browser Testing | ✔
Accessibility Testing | Optional
Performance Testing | Basic execution timing only
5. Test Environment
Item | Value
Application URL | https://qa-assessment.pages.dev/
OS | Windows 11 (or your OS)
Browser | Chrome
Browser | Firefox
Browser | Opera
Automation Tool | Playwright
Language | Java
Build Tool | Maven
Test Framework | JUnit 5
IDE | IntelliJ IDEA
6. Entry Criteria
Application is accessible.
Test environment is available.
Test data prepared.
Test cases completed.
Automation framework configured.
7. Exit Criteria
All critical test cases executed.
High severity defects documented.
Automation suite executes successfully.
Test report generated.
Deliverables completed.
8. Test Deliverables
Deliverable
Test Plan
Test Cases
Bug Report
Playwright Automation
GitHub Repository
README
Performance Report
Execution Report
9. Risks and Assumptions
Risk | Mitigation
Application unavailable | Retry testing later
UI changes | Use resilient locators
Dynamic elements | Explicit waits
Browser updates | Execute on multiple browsers
10. Roles and Responsibilities
Role | Responsibility
QA Engineer | Test planning
QA Engineer | Test design
QA Engineer | Automation
QA Engineer | Bug reporting
QA Engineer | Documentation
11. Test Schedule
Activity | Status
Test Planning | Completed
Test Case Design | Pending
Manual Testing | Pending
Automation Development | Pending
CI/CD Setup | Pending
Reporting | Pending
12. Test Data
Field | Valid Example | Invalid Example
First Name | John | John123
Email | john@test.com | john@test
Password | P@ssw0rd | 123
Phone | 1234567890 | abc123
LinkedIn | Valid LinkedIn profile URL | google.com
GitHub | Valid GitHub profile URL | github
13. Pass/Fail Criteria
Pass
Expected result matches the actual result.
Validation behaves correctly.
No unexpected errors occur.
Fail
Incorrect validation.
Missing validation.
Incorrect data accepted.
Application crash or unexpected behavior.